## Projects
ProjectID | ProjectName | StartDate | EndDate | DueDate | Status | Budget | ActualBudget | Clients | Department
P001 | ERP Implementation | 2024-01-01 | 2024-12-31 | 2025-02-20 | Completed | 500000 | 520000 | Matt Express | IT
P002 | Website Redesign | 2024-03-01 | 2024-08-30 | 2024-08-05 | In Progress | 80000 | 75000 | Nike | IT
P003 | CRM Migration | 2024-05-01 |  | 2024-12-25 | Completed | 430000 | 215000 | Adidas | IT
P004 | Data Warehouse Build | 2024-02-15 | 2024-10-15 | 2025-07-20 | In Progress | 300000 | 290000 | YMC | IT
P005 | Mobile App Launch | 2024-04-01 | 2024-09-30 | 2025-04-15 | In Progress | 150000 | 147000 | Linkedin | IT
P006 | Road Construction | 2025-08-20 |  | 2025-09-20 | In Progress | 8050000 | 2370000 | GRA | Construction
P007 | Office Renovation | 2024-06-03 |  | 2024-09-30 | Review | 320000 | 270000 | Georgia Power | Construction
P008 | Bridge Construction | 2025-09-04 |  | 2025-12-18 | In Progress | 3700000 | 133000 | GRA | Construction
P009 | Warehouse Facility | 2025-05-05 |  | 2025-11-19 | In Progress | 873000 | 419000 | Walmart | Construction
P010 | Product Launch Campaign | 2025-03-06 |  | 2025-04-06 | Review | 1250000 | 315600 | Microsoft | Marketing
P011 | Brand Awareness | 2024-08-07 |  | 2025-12-21 | In Progress | 3400000 | 1450000 | Amazon | Marketing
P012 | SEO Optimization | 2024-06-08 | 2025-03-17 | 2025-12-22 | Review | 300000 | 217000 | YMC | Marketing
P013 | Budget Planning | 2024-10-09 | 2025-04-07 | 2025-04-23 | Review | 450000 | 470000 | YMC | Finance
P014 | Audit Preparation | 2024-12-10 |  | 2025-04-20 | Review | 1550000 | 70000 | Georgia Power | Finance
P015 | Payroll Automation | 2024-09-11 |  | 2025-11-25 | In Progress | 375000 | 130000 | EDSON | Finance
P016 | Accounts Payable | 2024-07-12 |  | 2025-04-26 | Review | 220000 | 95000 | EDSON | Finance

## Tasks
TaskID | ProjectID | TaskName | EmplyeeID | StartDate | EndDate | DueDate | Status | %Complete | PlannedHours | ActualHours
T001 | P001 | Requirement Gathering | E001 | 2024-01-01 | 2024-02-10 | 2024-02-20 | Completed | 100 | 288 | 232
T002 | P002 | System Design | E002 | 2024-03-01 | 2024-07-23 | 2024-08-05 | Completed | 100 | 888 | 816
T003 | P003 | UI Wireframes | E003 | 2024-05-01 | 2024-11-12 | 2024-12-25 | Completed | 100 | 1360 | 1112
T004 | P004 | Data Migration | E004 | 2024-02-15 |  | 2024-07-20 | Blocked | 60 | 888 | 3336
T005 | P005 | Prototype Design | E005 | 2024-04-01 | 2025-02-14 | 2025-04-15 | Completed | 100 | 2168 | 1832
T006 | P006 | Clear and grade construction site | E006 | 2025-08-20 | 2025-09-15 | 2025-09-20 | Completed | 100 | 176 | 144
T007 | P007 | Install new flooring and lighting | E007 | 2024-06-03 | 2024-09-16 | 2024-09-30 | Completed | 100 | 680 | 600
T008 | P008 | Assemble steel reinforcement framework | E008 | 2025-09-04 |  | 2025-12-18 | In Progress | 40 | 600 | 96
T009 | P009 | Construct foundation and structural frame | E009 | 2025-05-05 | 2025-10-18 | 2025-11-19 | Completed | 100 | 1136 | 952
T010 | P010 | Create promotional materials | E010 | 2025-03-06 | 2025-05-19 | 2025-04-06 | Completed | 100 | 168 | 416
T011 | P011 | Run targeted social media ads | E011 | 2024-08-07 |  | 2025-12-21 | In Progress | 60 | 2856 | 2344
T012 | P012 | Perform keyword research and on-page SEO | E012 | 2024-06-08 | 2024-11-21 | 2025-12-22 | Completed | 100 | 3200 | 944
T013 | P013 | Collect departmental budget inputs | E013 | 2024-10-09 | 2025-02-22 | 2025-04-23 | Completed | 100 | 1120 | 776
T014 | P014 | Gather financial statements and records | E014 | 2024-12-10 | 2025-06-23 | 2025-04-20 | Completed | 100 | 744 | 1112
T015 | P015 | Configure payroll calculation engine | E015 | 2024-09-11 |  | 2025-11-25 | In Progress | 70 | 2512 | 2144
T016 | P016 | Implement invoice approval workflow | E016 | 2024-07-12 |  | 2025-04-26 | Blocked | 30 | 1640 | 2488
T017 | P001 | Conduct user training sessions | E017 | 2024-01-01 | 2024-04-26 | 2024-04-30 | Completed | 100 | 688 | 672
T018 | P002 | Migrate content to updated CMS | E018 | 2024-03-01 |  | 2025-04-28 | Blocked | 15 | 2408 | 3248
T019 | P003 | Integrate CRM with email system | E019 | 2024-05-01 | 2024-11-28 | 2024-10-29 | Completed | 100 | 1032 | 1208
T020 | P004 | Develop ETL pipelines for source systems | E020 | 2024-02-15 | 2024-04-29 | 2024-04-30 | Completed | 100 | 424 | 416
T021 | P005 | Deploy to iOS and Android stores | E021 | 2024-04-01 |  | 2025-11-30 | In Progress | 60 | 3472 | 3080
T022 | P006 | Lay asphalt and perform finishing work | E022 | 2025-08-20 |  | 2025-10-20 | In Progress | 70 | 344 | 184
T023 | P007 | Upgrade HVAC and electrical systems | E023 | 2024-06-03 | 2025-07-03 | 2025-06-03 | Review | 90 | 2088 | 2264
T024 | P008 | Pour and cure concrete deck | E024 | 2025-09-04 | 2025-10-04 | 2025-10-04 | Completed | 100 | 168 | 168
T025 | P009 | Install racking and storage systems | E025 | 2025-05-05 |  | 2025-10-05 | In Progress | 70 | 872 | 800
T026 | P010 | Host product launch event | E026 | 2025-03-06 | 2025-09-06 | 2025-09-15 | Review | 95 | 1096 | 1048
T027 | P011 | Organize influencer partnership program | E027 | 2024-08-07 | 2025-02-07 | 2025-02-28 | Completed | 100 | 1176 | 1056
T028 | P012 | Build high-quality backlinks | E028 | 2024-06-08 |  | 2024-12-08 | Blocked | 40 | 1032 | 2680
T029 | P013 | Prepare consolidated financial plan | E029 | 2024-10-09 | 2025-06-09 | 2025-05-09 | Review | 90 | 1216 | 1384
T030 | P014 | Review compliance checklists | E030 | 2024-12-10 | 2025-05-10 | 2025-05-10 | Review | 90 | 864 | 864
T031 | P015 | Test automated pay slip generation | E031 | 2024-09-11 | 2025-03-11 | 2025-04-11 | Review | 90 | 1216 | 1032
T032 | P016 | Automate vendor payment scheduling | E032 | 2024-07-12 | 2025-01-10 | 2025-03-10 | Review | 90 | 1368 | 1040
Formulas:
PlannedHours = (NETWORKDAYS([StartDate],[DueDate])-1)*8 + (MOD([DueDate],1)-MOD([StartDate],1))*24
ActualHours = (NETWORKDAYS([StartDate],IF([EndDate]<>"",[EndDate],TODAY()))-1)*8 + (MOD(IF([EndDate]<>"",[EndDate],TODAY()),1)-MOD([StartDate],1))*24

## Resources
ResourceID | EmployID | ProjectID | Name | Role | Department | HourlyRate | WorkedHours
RS001 | E001 | P001 | Sarah Lee | Business Analyst | IT | 60 | 232
RS002 | E002 | P002 | James Miller | Solution Architect | IT | 90 | 816
RS003 | E003 | P003 | Laura Green | UX Designer | IT | 70 | 1112
RS004 | E004 | P004 | Robert White | Data Engineer | IT | 80 | 3336
RS005 | E005 | P005 | Anna Black | Mobile Developer | IT | 75 | 1832
RS006 | E006 | P006 | Ethan Ramirez | Construction Manager | Engineering | 60 | 144
RS007 | E007 | P007 | Sophia Bennett | Facilities Manager | Engineering | 50 | 600
RS008 | E008 | P008 | Liam Carter | Civil Engineer | Engineering | 80 | 96
RS009 | E009 | P009 | Olivia Hughes | Operations Manager | Engineering | 80 | 952
RS010 | E010 | P010 | Noah Patel | Marketing Manager | Marketing | 70 | 416
RS011 | E011 | P011 | Ava Thompson | Marketing Manager | Marketing | 70 | 2344
RS012 | E012 | P012 | Mason Collins | Marketing Manager | Marketing | 70 | 944
RS013 | E013 | P013 | Isabella Wright | Financial Planning Manager | Finance | 80 | 776
RS014 | E014 | P014 | Lucas Mitchell | Audit Manager | Finance | 80 | 1112
RS015 | E015 | P015 | Mia Anderson | HR Manager | Human Resources | 70 | 2144
RS016 | E016 | P016 | Daniel Foster | HR Manager | Human Resources | 70 | 2488
RS017 | E017 | P001 | Jacob Harris | Business Analyst | IT | 60 | 672
RS018 | E018 | P002 | Emily Scott | Solution Architect | IT | 90 | 3248
RS019 | E019 | P003 | Alexander Ross | UX Designer | IT | 70 | 1208
RS020 | E020 | P004 | Grace Morgan | Data Engineer | IT | 80 | 416
RS021 | E021 | P005 | Benjamin Ward | Mobile Developer | IT | 75 | 3080
RS022 | E022 | P006 | Chloe Turner | Construction Manager | Engineering | 60 | 184
RS023 | E023 | P007 | Elijah Brooks | Facilities Manager | Engineering | 50 | 2264
RS024 | E024 | P008 | Harper Lee | Civil Engineer | Engineering | 80 | 168
RS025 | E025 | P009 | Matthew Price | Operations Manager | Engineering | 80 | 800
RS026 | E026 | P010 | Aria Kelly | Marketing Manager | Marketing | 70 | 1048
RS027 | E027 | P011 | William Sanders | Marketing Manager | Marketing | 70 | 1056
RS028 | E028 | P012 | Zoe Richardson | Marketing Manager | Marketing | 70 | 2680
RS029 | E029 | P013 | James Coleman | Financial Planning Manager | Finance | 80 | 1384
RS030 | E030 | P014 | Lily Parker | Audit Manager | Finance | 80 | 864
RS031 | E031 | P015 | Henry Diaz | HR Manager | Human Resources | 70 | 1032
RS032 | E032 | P016 | Natalie Murphy | HR Manager | Human Resources | 70 | 1040

## Budget
BudgetID | ProjectID | Project | ProjectedBudget | ActualBudget
B130 | P001 | ERP Implementation | 500000 | 520000
B131 | P002 | Website Redesign | 80000 | 75000
B132 | P003 | CRM Migration | 430000 | 215000
B133 | P004 | Data Warehouse Build | 300000 | 290000
B134 | P005 | Mobile App Launch | 150000 | 147000
B135 | P006 | Road Construction | 8050000 | 2370000
B136 | P007 | Office Renovation | 320000 | 270000
B137 | P008 | Bridge Construction | 3700000 | 133000
B138 | P009 | Warehouse Facility | 873000 | 419000
B139 | P010 | Product Launch Campaign | 1250000 | 315600
B140 | P011 | Brand Awareness | 3400000 | 1450000
B141 | P012 | SEO Optimization | 300000 | 217000
B142 | P013 | Budget Planning | 450000 | 470000
B143 | P014 | Audit Preparation | 1550000 | 70000
B144 | P015 | Payroll Automation | 375000 | 130000
B145 | P016 | Accounts Payable | 220000 | 95000

## Invoice
InvoiceID | ProjectID | InvoiceDate | DueDate | Amount | InvoiceStatus | PaidDate | Notes
INV001 | P001 | 1/15/2024 | 2/15/2024 | 120000 | Paid | 2/10/2024 | Initial ERP implementation payment
INV002 | P001 | 6/1/2024 | 7/1/2024 | 200000 | Paid | 6/25/2024 | Mid-project milestone
INV003 | P001 | 11/30/2024 | 12/30/2024 | 200000 | Overdue |  | Final payment pending
INV004 | P002 | 3/15/2024 | 4/15/2024 | 30000 | Paid | 4/10/2024 | Website redesign kickoff
INV005 | P002 | 8/15/2024 | 9/15/2024 | 50000 | Pending |  | Awaiting client approval
INV006 | P006 | 9/1/2025 | 10/1/2025 | 1500000 | Pending |  | Road construction first milestone
INV007 | P010 | 3/20/2025 | 4/20/2025 | 600000 | Paid | 4/18/2025 | Campaign setup
INV008 | P010 | 7/1/2025 | 8/1/2025 | 650000 | Pending |  | Campaign execution balance
INV009 | P013 | 10/20/2024 | 11/20/2024 | 200000 | Paid | 11/15/2024 | Budget planning installment
INV010 | P013 | 3/1/2025 | 4/1/2025 | 250000 | Pending |  | Final payment
INV011 | P007 | 6/10/2024 | 7/10/2024 | 100000 | Paid | 7/5/2024 | Office renovation phase 1
INV012 | P007 | 8/15/2024 | 9/15/2024 | 170000 | Pending |  | Office renovation final phase
INV013 | P008 | 9/15/2025 | 10/15/2025 | 1200000 | Pending |  | Bridge construction milestone 1
INV014 | P008 | 11/1/2025 | 12/1/2025 | 2500000 | Pending |  | Bridge construction milestone 2
INV015 | P009 | 5/20/2025 | 6/20/2025 | 200000 | Paid | 6/18/2025 | Warehouse racking installation
INV016 | P009 | 7/1/2025 | 8/1/2025 | 219000 | Pending |  | Warehouse facility final payment
INV017 | P011 | 8/20/2024 | 9/20/2024 | 700000 | Paid | 9/15/2024 | Brand awareness social campaign
INV018 | P011 | 12/1/2024 | 12/31/2024 | 750000 | Pending |  | Influencer marketing campaign
INV019 | P012 | 6/15/2024 | 7/15/2024 | 120000 | Paid | 7/10/2024 | SEO website optimization
INV020 | P012 | 1/10/2025 | 2/10/2025 | 97000 | Pending |  | SEO backlink campaign
INV021 | P014 | 12/20/2024 | 1/20/2025 | 35000 | Paid | 1/15/2025 | Audit prep document review
INV022 | P014 | 2/10/2025 | 3/10/2025 | 35000 | Pending |  | Final audit submission
INV023 | P015 | 9/20/2024 | 10/20/2024 | 65000 | Paid | 10/18/2024 | Payroll automation initial phase
INV024 | P015 | 11/5/2024 | 12/5/2024 | 65000 | Pending |  | Payroll automation final phase
INV025 | P016 | 7/20/2024 | 8/20/2024 | 45000 | Paid | 8/18/2024 | Accounts payable workflow setup
INV026 | P016 | 9/1/2024 | 10/1/2024 | 50000 | Pending |  | Final AP automation payment

## Risks
RiskID | ProjectID | Severity | Status
RS701 | P001 | Low | Mitigated
RS702 | P002 | Low | Mitigated
RS703 | P003 | High | Open
RS704 | P004 | Low | Mitigated
RS705 | P005 | Medium | Open
RS706 | P006 | High | Open
RS707 | P007 | Low | Mitigated
RS708 | P008 | Medium | Mitigated
RS709 | P009 | High | Open
RS710 | P010 | Low | Mitigated
RS711 | P011 | High | Mitigated
RS712 | P012 | Medium | Mitigated
RS713 | P013 | Low | Mitigated
RS714 | P014 | Low | Mitigated
RS715 | P015 | Low | Mitigated
RS716 | P016 | Low | Mitigated